## Pre-Development
Task | Optimistic | Most Likely | Pessimistic | Risk | Estimate
Pre-Development
Project Kickoff
High – Level Business Requirements
Hold requirements elicitation sessions | 3 | 5 | 8 | High | 8
Document High level business requirements | 3 | 4 | 6 | High | 6
Review / approve high-level business requirements | 1 | 2 | 3 | High | 3
Project Schedule
Meet with appropriate teams to get preliminary estimates | 2 | 3 | 4 | Medium | 3 | To Estimate Effort 1. Estimate the Optimistic, Most Likely, and Pessimistic task duration, if ONE PERSON was performing that task 2. Estimate the risk of each task  For example, the business analysis is high-risk, as we need to determine requirements with great care & attention to detail 3. Use the risk-factor to select the estimate  A high-risk task would use the most pessimistic estimate; a medium-risk the most likely estimate, and  A low-risk task would use the Optimistic estimate
Documentation project timeline (including dependencies) | 3 | 5 | 8 | Medium | 5
Review project schedule | 2 | 3 | 4 | Medium | 3
Project resource requests
Put in requests for resources | 1 | 1 | 1 | Low | 1
Get resources assigned | 1 | 2 | 3 | Low | 1
Funding Release
Creation of Funding Release | 3 | 5 | 8 | High | 8
Review of Funding Release | 1 | 2 | 3 | High | 3
Approval of Funding Release | 1 | 2 | 3 | High | 3
Infrastructure Setup
Database Software
Request quotation from vendors | 1 | 2 | 3 | Low | 1
Purchase licenses | 1 | 3 | 5 | Low | 1
License installers / keys delivered | 3 | 5 | 8 | Low | 3
Performance Testing
Identification of performance testing tool | 1 | 1 | 1 | Low | 1
Request quotation from vendors | 1 | 2 | 3 | Low | 1
Purchase licenses | 1 | 3 | 4 | Low | 1
License installers / keys delivered | 3 | 5 | 8 | Low | 3
Servers
Request quotation from vendors for hardware | 1 | 2 | 3 | Low | 1
Purchase servers | 1 | 3 | 4 | Low | 1
Servers allocated | 3 | 5 | 8 | Low | 3
Access granted to users
Code Repository Tool
Identification of code repository tool
Request quotation from vendors
Purchase licenses
License installers / keys delivered
Access granted to users
Software Installed / verified on developers laptops
Security Scanning Tool
Identification of scanning tool
Request quotation from vendors
Purchase licenses
License installers / keys delivered
Access created to users
Software Installed / verified on necessary machines
Continuous integration/continuous deployment tool
Identification of tool
Request quotation from vendors
Purchase licenses
License installers / keys delivered
Software installed / verified

## Phase 2
Task | Optimistic | Most Likely | Pessimistic | Risk | Estimate
Phase 2
Develop Patient Facing Record History
DBMS:
Install & Configure DBMS Engine & SQL Interface | 5 | 8 | 12 | Medium | 8 | To Estimate Effort 1. Estimate the Optimistic, Most Likely, and Pessimistic task duration, if ONE PERSON was performing that task 2. Estimate the risk of each task  For example, the business analysis is high-risk, as we need to determine requirements with great care & attention to detail 3. Use the risk-factor to select the estimate  A high-risk task would use the most pessimistic estimate; a medium-risk the most likely estimate, and  A low-risk task would use the Optimistic estimate
Test SQL interface software | 2 | 3 | 4 | Medium | 3
REST API Service Server:
Requirements
Requirements Elicitation | 3 | 5 | 8 | High | 8
Documentation of requirements | 3 | 4 | 6 | High | 6
Review requirements | 1 | 2 | 3 | High | 3
Software Design
Create design document | 3 | 5 | 8 | High | 8
Review of design | 1 | 3 | 5 | High | 5
Software Development
Development of software | 5 | 8 | 12 | High | 12
Code Review | 2 | 3 | 4 | High | 4
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 1 | 3 | 5 | Medium | 3
Client App:
Requirements
Requirements Elicitation | 3 | 5 | 8 | High | 8
Documentation of requirements | 3 | 4 | 6 | High | 6
Review requirements | 1 | 2 | 3 | High | 3
User Interface design
Initial Wireframe design | 5 | 8 | 12 | Low | 5
Review of wireframe | 1 | 3 | 5 | Low | 1
Create design based off feedback | 3 | 5 | 8 | Low | 3
Review design | 1 | 3 | 5 | Low | 1
Software Design
Create design document | 3 | 5 | 8 | High | 8
Review of design | 1 | 3 | 5 | High | 5
Software Development
Development of software | 5 | 8 | 12 | High | 12
Code Review | 2 | 3 | 4 | High | 4
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 3 | 5 | 8 | Medium | 5
System Integration Testing
Creation of System Integration Test Cases | 3 | 5 | 8 | Medium | 5
Execution of System Integration Test Cases | 5 | 8 | 12 | Medium | 8
Develop Patient Facing Appointment Module
DBMS:
Install & Configure DBMS Engine & SQL Interface | 5 | 8 | 12 | Medium | 8
Test SQL interface software | 2 | 3 | 4 | Medium | 3
REST API Service Server:
Requirements
Requirements Elicitation | 3 | 5 | 8 | High | 8
Documentation of requirements | 3 | 4 | 6 | High | 6
Review requirements | 1 | 2 | 3 | High | 3
Software Design
Create design document | 3 | 5 | 8 | High | 8
Review of design | 1 | 3 | 5 | High | 5
Software Development
Development of software | 5 | 8 | 12 | High | 12
Code Review | 2 | 3 | 4 | High | 4
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 3 | 5 | 8 | Medium | 5
Client App:
Requirements
Requirements Elicitation | 3 | 5 | 8 | High | 8
Documentation of requirements | 3 | 4 | 6 | High | 6
Review requirements | 1 | 2 | 3 | High | 3
User Interface design
Initial Wireframe design | 5 | 8 | 12 | Low | 5
Review of wireframe | 1 | 3 | 5 | Low | 1
Create design based off feedback | 3 | 5 | 8 | Low | 3
Review design | 1 | 3 | 5 | Low | 1
Software Design
Create design document | 3 | 5 | 8 | High | 8
Review of design | 1 | 3 | 5 | High | 5
Software Development
Development of software | 5 | 8 | 12 | High | 12
Code Review | 2 | 3 | 4 | High | 4
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 3 | 5 | 8 | Medium | 5
System Integration Testing
Creation of System Integration Test Cases | 3 | 5 | 8 | Medium | 5
Execution of System Integration Test Cases | 5 | 8 | 12 | Medium | 8
Develop Patient Self Service Check-in
DBMS:
Install & Configure DBMS Engine & SQL Interface | 5 | 8 | 12 | Medium | 8
Test SQL interface software | 2 | 3 | 4 | Medium | 3
REST API Service Server:
Requirements
Requirements Elicitation | 3 | 5 | 8 | High | 8
Documentation of requirements | 3 | 4 | 6 | High | 6
Review requirements | 1 | 2 | 3 | High | 3
Software Design
Create design document | 3 | 5 | 8 | High | 8
Review of design | 1 | 3 | 5 | High | 5
Software Development
Development of software | 5 | 8 | 12 | High | 12
Code Review | 2 | 3 | 4 | High | 4
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 3 | 5 | 8 | Medium | 5
Client App:
Requirements
Requirements Elicitation | 3 | 5 | 8 | High | 8
Documentation of requirements | 3 | 4 | 6 | High | 6
Review requirements | 1 | 2 | 3 | High | 3
User Interface design
Initial Wireframe design | 5 | 8 | 12 | Low | 5
Review of wireframe | 1 | 3 | 5 | Low | 1
Create design based off feedback | 3 | 5 | 8 | Low | 3
Review design | 1 | 3 | 5 | Low | 1
Software Design
Create design document | 3 | 5 | 8 | High | 8
Review of design | 1 | 3 | 5 | High | 5
Software Development
Development of software | 5 | 8 | 12 | High | 12
Code Review | 2 | 3 | 4 | High | 4
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 3 | 5 | 8 | Medium | 5
System Integration Testing
Creation of System Integration Test Cases | 3 | 5 | 8 | Medium | 5
Execution of System Integration Test Cases | 5 | 8 | 12 | Medium | 8
Vulnerability Assessment
Execution of vulnerability scan | 5 | 8 | 12 | High | 12
Creation of reports | 3 | 5 | 8 | High | 8
Vulnerability remediation by development team | 10 | 15 | 18 | High | 18
Re-scan for vulnerabilities | 3 | 5 | 8 | High | 8
Final report created | 2 | 3 | 4 | High | 4
Performance Testing
Creation of Performance Test Cases | 3 | 5 | 8 | Medium | 5
Execution of test cases | 5 | 8 | 12 | Medium | 8
Regression Testing
Creation of regression suite of test cases |  |  |  | Medium
Execution of regression suite |  |  |  | Medium
User Acceptance Testing
Creation of User Acceptance Testing |  |  |  | Medium
Execution of User Acceptance testing |  |  |  | Medium
Client sign off for testing |  |  |  | Medium
System Training
Develop training materials and resources |  |  |  | Medium
Staff training |  |  |  | Medium
Staff workshops |  |  |  | Medium
Deployment
Creation of rollout plan |  |  |  | High
Review of roll out plan |  |  |  | High
Dry-run of roll out plan |  |  |  | High
Execution of rollout |  |  |  | High