## Pre Development
Task | Optimistic | Most Likely | Pessimistic | Risk | Estimate
Pre-Development
Project Kickoff
High – Level Business Requirements
Hold requirements elicitation sessions | 3 | 5 | 8 | High | 8
Document High level business requirements | 3 | 4 | 6 | High | 6
Review / approve high-level business requirements | 1 | 2 | 3 | High | 3
Project Schedule
Meet with appropriate teams to get preliminary estimates | 2 | 3 | 4 | Medium | 3
Documentation project timeline (including dependencies) | 3 | 5 | 8 | Medium | 5
Review project schedule | 2 | 3 | 4 | Medium | 3
Project resource requests
Put in requests for resources | 1 | 1 | 1 | Low | 1
Get resources assigned | 1 | 2 | 3 | Low | 1
Funding Release
Creation of Funding Release | 3 | 5 | 8 | High | 8
Review of Funding Release | 1 | 2 | 3 | High | 3
Approval of Funding Release | 1 | 2 | 3 | High | 3
Infrastructure Setup
Database Software
Request quotation from vendors | 1 | 2 | 3 | Low | 1
Purchase licenses | 1 | 3 | 5 | Low | 1
License installers / keys delivered | 3 | 5 | 8 | Low | 3
Performance Testing
Identification of performance testing tool | 1 | 1 | 1 | Low | 1
Request quotation from vendors | 1 | 2 | 3 | Low | 1
Purchase licenses | 1 | 3 | 4 | Low | 1
License installers / keys delivered | 3 | 5 | 8 | Low | 3
Servers
Request quotation from vendors for hardware | 1 | 2 | 3 | Low | 1
Purchase servers | 1 | 3 | 4 | Low | 1
Servers allocated | 3 | 5 | 8 | Low | 3
Access granted to users
Code Repository Tool
Identification of code repository tool | 2 | 3 | 4 | Medium | 3
Request quotation from vendors | 1 | 2 | 3 | Low | 2
Purchase licenses | 2 | 3 | 4 | Low | 3
License installers / keys delivered | 1 | 1 | 2 | Low | 1
Access granted to users | 1 | 2 | 3 | Medium | 2
Software Installed / verified on developers laptops | 2 | 3 | 5 | Medium | 3
Security Scanning Tool
Identification of scanning tool | 2 | 3 | 4 | Medium | 3
Request quotation from vendors | 1 | 2 | 3 | Low | 2
Purchase licenses | 2 | 3 | 4 | Low | 3
License installers / keys delivered | 1 | 1 | 2 | Low | 1
Access created to users | 1 | 2 | 3 | Medium | 2
Software Installed / verified on necessary machines | 2 | 3 | 5 | Medium | 3
Continuous integration/continuous deployment tool
Identification of tool | 2 | 3 | 4 | Medium | 3
Request quotation from vendors | 1 | 2 | 3 | Low | 2
Purchase licenses | 2 | 3 | 4 | Low | 3
License installers / keys delivered | 1 | 1 | 2 | Low | 1
Software installed / verified | 2 | 3 | 5 | Medium | 3

## Phase 1
Task | Optimistic | Most Likely | Pessimistic | Risk | Estimate
Phase 1
Develop Appointment module
DBMS:
Install & Configure DBMS Engine & SQL Interface | 3 | 5 | 8 | Medium | 5
Test SQL interface software | 1 | 2 | 4 | Medium | 2
REST API Service Server:
Requirements
Requirements gathering | 2 | 3 | 4 | Medium | 3
Documentation of requirements | 3 | 4 | 5 | Medium | 4
Review requirements | 1 | 2 | 3 | Low | 1
Software Design
Create design document | 5 | 6 | 8 | High | 8
Review of design | 2 | 3 | 4 | Medium | 3
Software Development
Development of software | 5 | 8 | 10 | High | 10
Code Review | 2 | 3 | 4 | High | 4
Unit Testing
Creation of test cases | 1 | 2 | 3 | Medium | 2
Execution of test cases | 2 | 4 | 5 | Medium | 4
Client App:
Requirements
Requirements Elicitation | 3 | 5 | 6 | Medium | 5
Documentation of requirements | 3 | 4 | 5 | Medium | 4
Review requirements | 2 | 3 | 4 | Low | 2
User Interface design
Initial Wireframe design | 2 | 4 | 5 | Low | 2
Review of wireframe | 1 | 2 | 3 | Low | 1
Create design based off feedback | 2 | 5 | 6 | High | 6
Review design | 1 | 2 | 3 | Low | 1
Software Design
Create design document | 3 | 5 | 6 | High | 6
Review of design | 2 | 3 | 4 | High | 4
Software Development
Development of software | 5 | 8 | 10 | High | 10
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 1 | 2 | 3 | Medium | 2
Execution of test cases | 3 | 4 | 5 | Medium | 4
System Integration Testing
Creation of System Integration Test Cases | 2 | 3 | 4 | Medium | 3
Execution of System Integration Test Cases | 5 | 6 | 7 | Medium | 6
Develop employee records module
DBMS:
Install & Configure DBMS Engine & SQL Interface | 4 | 7 | 10 | Medium | 7
Test SQL interface software | 2 | 3 | 4 | Medium | 3
REST API Service Server:
Requirements
Requirements Elicitation | 2 | 3 | 4 | High | 4
Documentation of requirements | 2 | 3 | 5 | Medium | 3
Review requirements | 2 | 3 | 5 | Medium | 3
Software Design
Create design document | 3 | 5 | 8 | High | 8
Review of design | 2 | 3 | 4 | High | 4
Software Development
Development of software | 5 | 8 | 10 | High | 10
Code Review | 2 | 3 | 4 | High | 4
Unit Testing
Creation of test cases | 1 | 2 | 3 | Medium | 2
Execution of test cases | 2 | 3 | 4 | Medium | 3
Client App:
Requirements
Requirements Elicitation | 2 | 3 | 4 | Medium | 3
Documentation of requirements | 2 | 3 | 4 | High | 4
Review requirements | 1 | 2 | 3 | Medium | 2
User Interface design
Initial Wireframe design | 3 | 4 | 5 | Medium | 4
Review of wireframe | 2 | 3 | 4 | Medium | 3
Create design based off feedback | 4 | 5 | 7 | High | 7
Review design | 2 | 3 | 4 | Low | 2
Software Design
Create design document | 2 | 5 | 8 | High | 8
Review of design | 1 | 3 | 5 | Medium | 3
Software Development
Development of software | 3 | 6 | 9 | High | 9
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 1 | 2 | 3 | Medium | 2
Execution of test cases | 5 | 6 | 7 | Medium | 6
System Integration Testing
Creation of System Integration Test Cases | 2 | 3 | 4 | Medium | 3
Execution of System Integration Test Cases | 5 | 6 | 8 | Medium | 6
Develop Patient records module
DBMS:
Install & Configure DBMS Engine & SQL Interface | 4 | 6 | 9 | High | 9
Test SQL interface software | 2 | 3 | 4 | Medium | 3
REST API Service Server:
Requirements
Requirements Elicitation | 2 | 3 | 4 | High | 4
Documentation of requirements | 3 | 5 | 6 | High | 6
Review requirements | 3 | 4 | 5 | Medium | 4
Software Design
Create design document | 2 | 5 | 6 | High | 6
Review of design | 2 | 3 | 4 | Medium | 3
Software Development
Development of software | 4 | 6 | 10 | High | 10
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 4 | 5 | 6 | Medium | 5
Client App:
Requirements
Requirements Elicitation | 2 | 3 | 4 | High | 4
Documentation of requirements | 5 | 6 | 7 | High | 7
Review requirements | 1 | 2 | 3 | Medium | 2
User Interface design
Initial Wireframe design | 3 | 4 | 5 | Medium | 4
Review of wireframe | 2 | 3 | 4 | Low | 2
Create design based off feedback | 2 | 4 | 6 | High | 6
Review design | 2 | 4 | 5 | Low | 2
Software Design
Create design document | 3 | 4 | 6 | High | 6
Review of design | 1 | 3 | 4 | Medium | 3
Software Development
Development of software | 4 | 6 | 8 | High | 8
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 2 | 5 | 6 | Medium | 5
System Integration Testing
Creation of System Integration Test Cases | 2 | 3 | 4 | Medium | 3
Execution of System Integration Test Cases | 3 | 4 | 5 | Medium | 4
Develop Inventory Management Module
DBMS:
Install & Configure DBMS Engine & SQL Interface | 4 | 6 | 9 | High | 9
Test SQL interface software | 2 | 3 | 4 | Medium | 3
REST API Service Server:
Requirements
Requirements Elicitation | 2 | 3 | 4 | High | 4
Documentation of requirements | 3 | 5 | 6 | High | 6
Review requirements | 3 | 4 | 5 | Medium | 4
Software Design
Create design document | 2 | 5 | 6 | High | 6
Review of design | 2 | 3 | 4 | Medium | 3
Software Development
Development of software | 4 | 6 | 10 | High | 10
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 4 | 5 | 6 | Medium | 5
Client App:
Requirements
Requirements Elicitation | 2 | 3 | 4 | High | 4
Documentation of requirements | 5 | 6 | 7 | High | 7
Review requirements | 1 | 2 | 3 | Medium | 2
User Interface design
Initial Wireframe design | 3 | 4 | 5 | Medium | 4
Review of wireframe | 2 | 3 | 4 | Low | 2
Create design based off feedback | 2 | 4 | 6 | High | 6
Review design | 2 | 4 | 5 | Low | 2
Software Design
Create design document | 3 | 4 | 6 | High | 6
Review of design | 1 | 3 | 4 | Medium | 3
Software Development
Development of software | 4 | 6 | 8 | High | 8
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 2 | 5 | 6 | Medium | 5
System Integration Testing
Creation of System Integration Test Cases | 2 | 3 | 4 | Medium | 3
Execution of System Integration Test Cases | 3 | 4 | 5 | Medium | 4
Vulnerability Assessment
Execution of vulnerability scan | 5 | 8 | 10 | High | 10
Creation of reports | 1 | 2 | 3 | Medium | 2
Vulnerability remediation by development team | 4 | 5 | 8 | High | 8
Re-scan for vulnerabilities | 2 | 5 | 7 | High | 7
Final report created | 2 | 3 | 4 | Medium | 3
Performance Testing
Creation of Performance Test Cases | 3 | 5 | 8 | Medium | 5
Execution of test cases | 5 | 8 | 10 | Medium | 8
Regression Testing
Creation of regression suite of test cases | 3 | 4 | 7 | Medium | 4
Execution of regression suite | 6 | 7 | 9 | Medium | 7
User Acceptance Testing
Creation of User Acceptance Testing | 2 | 3 | 5 | Medium | 3
Execution of User Acceptance testing | 5 | 7 | 9 | Medium | 7
Client sign off for testing | 1 | 1 | 2 | Low | 1
System Training
Develop training materials and resources | 5 | 8 | 10 | Medium | 8
Staff training | 2 | 3 | 4 | Medium | 3
Staff workshops | 1 | 2 | 3 | Medium | 2
Deployment
Creation of rollout plan | 2 | 3 | 4 | High | 4
Review of roll out plan | 1 | 1 | 2 | High | 2
Dry-run of roll out plan | 1 | 1 | 2 | High | 2
Execution of rollout | 1 | 1 | 2 | High | 2

## Phase 2
Task | Optimistic | Most Likely | Pessimistic | Risk | Estimate
Phase 2
Develop Patient Facing Record History
DBMS:
Install & Configure DBMS Engine & SQL Interface | 3 | 5 | 8 | Medium | 5
Test SQL interface software | 1 | 2 | 4 | Medium | 2
REST API Service Server:
Requirements
Requirements Elicitation | 2 | 3 | 4 | Medium | 3
Documentation of requirements | 3 | 4 | 5 | Medium | 4
Review requirements | 1 | 2 | 3 | Low | 1
Software Design
Create design document | 5 | 6 | 8 | High | 8
Review of design | 2 | 3 | 4 | Medium | 3
Software Development
Development of software | 5 | 8 | 10 | High | 10
Code Review | 2 | 3 | 4 | High | 4
Unit Testing
Creation of test cases | 1 | 2 | 3 | Medium | 2
Execution of test cases | 2 | 4 | 5 | Medium | 4
Client App:
Requirements
Requirements Elicitation | 3 | 5 | 6 | Medium | 5
Documentation of requirements | 3 | 4 | 5 | Medium | 4
Review requirements | 2 | 3 | 4 | Low | 2
User Interface design
Initial Wireframe design | 2 | 4 | 5 | Low | 2
Review of wireframe | 1 | 2 | 3 | Low | 1
Create design based off feedback | 2 | 5 | 6 | High | 6
Review design | 1 | 2 | 3 | Low | 1
Software Design
Create design document | 3 | 5 | 6 | High | 6
Review of design | 2 | 3 | 4 | High | 4
Software Development
Development of software | 5 | 8 | 10 | High | 10
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 1 | 2 | 3 | Medium | 2
Execution of test cases | 3 | 4 | 5 | Medium | 4
System Integration Testing
Creation of System Integration Test Cases | 2 | 3 | 4 | Medium | 3
Execution of System Integration Test Cases | 5 | 6 | 7 | Medium | 6
Develop Patient Facing Appointment Module
DBMS:
Install & Configure DBMS Engine & SQL Interface | 4 | 7 | 10 | Medium | 7
Test SQL interface software | 2 | 3 | 4 | Medium | 3
REST API Service Server:
Requirements
Requirements Elicitation | 2 | 3 | 4 | High | 4
Documentation of requirements | 2 | 3 | 5 | Medium | 3
Review requirements | 2 | 3 | 5 | Medium | 3
Software Design
Create design document | 3 | 5 | 8 | High | 8
Review of design | 2 | 3 | 4 | High | 4
Software Development
Development of software | 5 | 8 | 10 | High | 10
Code Review | 2 | 3 | 4 | High | 4
Unit Testing
Creation of test cases | 1 | 2 | 3 | Medium | 2
Execution of test cases | 2 | 3 | 4 | Medium | 3
Client App:
Requirements
Requirements Elicitation | 2 | 3 | 4 | Medium | 3
Documentation of requirements | 2 | 3 | 4 | High | 4
Review requirements | 1 | 2 | 3 | Medium | 2
User Interface design
Initial Wireframe design | 3 | 4 | 5 | Medium | 4
Review of wireframe | 2 | 3 | 4 | Medium | 3
Create design based off feedback | 4 | 5 | 7 | High | 7
Review design | 2 | 3 | 4 | Low | 2
Software Design
Create design document | 2 | 5 | 8 | High | 8
Review of design | 1 | 3 | 5 | Medium | 3
Software Development
Development of software | 3 | 6 | 9 | High | 9
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 1 | 2 | 3 | Medium | 2
Execution of test cases | 5 | 6 | 7 | Medium | 6
System Integration Testing
Creation of System Integration Test Cases | 2 | 3 | 4 | Medium | 3
Execution of System Integration Test Cases | 5 | 6 | 8 | Medium | 6
Develop Patient Self Service Check-in
DBMS:
Install & Configure DBMS Engine & SQL Interface | 4 | 6 | 9 | High | 9
Test SQL interface software | 2 | 3 | 4 | Medium | 3
REST API Service Server:
Requirements
Requirements Elicitation | 2 | 3 | 4 | High | 4
Documentation of requirements | 3 | 5 | 6 | High | 6
Review requirements | 3 | 4 | 5 | Medium | 4
Software Design
Create design document | 2 | 5 | 6 | High | 6
Review of design | 2 | 3 | 4 | Medium | 3
Software Development
Development of software | 4 | 6 | 10 | High | 10
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 4 | 5 | 6 | Medium | 5
Client App:
Requirements
Requirements Elicitation | 2 | 3 | 4 | High | 4
Documentation of requirements | 5 | 6 | 7 | High | 7
Review requirements | 1 | 2 | 3 | Medium | 2
User Interface design
Initial Wireframe design | 3 | 4 | 5 | Medium | 4
Review of wireframe | 2 | 3 | 4 | Low | 2
Create design based off feedback | 2 | 4 | 6 | High | 6
Review design | 2 | 4 | 5 | Low | 2
Software Design
Create design document | 3 | 4 | 6 | High | 6
Review of design | 1 | 3 | 4 | Medium | 3
Software Development
Development of software | 4 | 6 | 8 | High | 8
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 2 | 5 | 6 | Medium | 5
System Integration Testing
Creation of System Integration Test Cases | 2 | 3 | 4 | Medium | 3
Execution of System Integration Test Cases | 3 | 4 | 5 | Medium | 4
Vulnerability Assessment
Execution of vulnerability scan | 5 | 8 | 10 | High | 10
Creation of reports | 1 | 2 | 3 | Medium | 2
Vulnerability remediation by development team | 4 | 5 | 8 | High | 8
Re-scan for vulnerabilities | 2 | 5 | 7 | High | 7
Final report created | 2 | 3 | 4 | Medium | 3
Performance Testing
Creation of Performance Test Cases | 3 | 5 | 8 | Medium | 5
Execution of test cases | 5 | 8 | 10 | Medium | 8
Regression Testing
Creation of regression suite of test cases | 3 | 4 | 7 | Medium | 4
Execution of regression suite | 6 | 7 | 9 | Medium | 7
User Acceptance Testing
Creation of User Acceptance Testing | 2 | 3 | 5 | Medium | 3
Execution of User Acceptance testing | 5 | 7 | 9 | Medium | 7
Client sign off for testing | 1 | 1 | 2 | Low | 1
System Training
Develop training materials and resources | 5 | 8 | 10 | Medium | 8
Staff training | 2 | 3 | 4 | Medium | 3
Staff workshops | 1 | 2 | 3 | Medium | 2
Deployment
Creation of rollout plan | 2 | 3 | 4 | High | 4
Review of roll out plan | 1 | 1 | 2 | High | 2
Dry-run of roll out plan | 1 | 1 | 2 | High | 2
Execution of rollout | 1 | 1 | 2 | High | 2

## Phase 3
Task | Optimistic | Most Likely | Pessimistic | Risk | Estimate
Phase 3
Develop report generation module
DBMS:
Install & Configure DBMS Engine & SQL Interface | 3 | 5 | 8 | Medium | 5
Test SQL interface software | 1 | 2 | 4 | Medium | 2
REST API Service Server:
Requirements
Requirements gathering | 2 | 3 | 4 | Medium | 3 | To Estimate Effort 1. Estimate the Optimistic, Most Likely, and Pessimistic task duration, if ONE PERSON was performing that task 2. Estimate the risk of each task  For example, the business analysis is high-risk, as we need to determine requirements with great care & attention to detail 3. Use the risk-factor to select the estimate  A high-risk task would use the most pessimistic estimate; a medium-risk the most likely estimate, and  A low-risk task would use the Optimistic estimate
Documentation of requirements | 3 | 4 | 5 | Medium | 4
Review requirements | 1 | 2 | 3 | Low | 1
Software Design
Create design document | 5 | 6 | 8 | High | 8
Review of design | 2 | 3 | 4 | Medium | 3
Software Development
Development of software | 5 | 8 | 10 | High | 10
Code Review | 2 | 3 | 4 | High | 4
Unit Testing
Creation of test cases | 1 | 2 | 3 | Medium | 2
Execution of test cases | 2 | 4 | 5 | Medium | 4
Client App:
Requirements
Requirements Elicitation | 3 | 5 | 6 | Medium | 5
Documentation of requirements | 3 | 4 | 5 | Medium | 4
Review requirements | 2 | 3 | 4 | Low | 2
User Interface design
Initial Wireframe design | 2 | 4 | 5 | Low | 2
Review of wireframe | 1 | 2 | 3 | Low | 1 |  | *This information is taken from the lecture slides
Create design based off feedback | 2 | 5 | 6 | High | 6
Review design | 1 | 2 | 3 | Low | 1
Software Design
Create design document | 3 | 5 | 6 | High | 6
Review of design | 2 | 3 | 4 | High | 4
Software Development
Development of software | 5 | 8 | 10 | High | 10
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 1 | 2 | 3 | Medium | 2
Execution of test cases | 3 | 4 | 5 | Medium | 4
System Integration Testing
Creation of System Integration Test Cases | 2 | 3 | 4 | Medium | 3
Execution of System Integration Test Cases | 5 | 6 | 7 | Medium | 6
Develop external inventory management module
DBMS:
Install & Configure DBMS Engine & SQL Interface | 4 | 7 | 10 | Medium | 7
Test SQL interface software | 2 | 3 | 4 | Medium | 3
REST API Service Server:
Requirements
Requirements Elicitation | 2 | 3 | 4 | High | 4
Documentation of requirements | 2 | 3 | 5 | Medium | 3
Review requirements | 2 | 3 | 5 | Medium | 3
Software Design
Create design document | 3 | 5 | 8 | High | 8
Review of design | 2 | 3 | 4 | High | 4
Software Development
Development of software | 5 | 8 | 10 | High | 10
Code Review | 2 | 3 | 4 | High | 4
Unit Testing
Creation of test cases | 1 | 2 | 3 | Medium | 2
Execution of test cases | 2 | 3 | 4 | Medium | 3
Client App:
Requirements
Requirements Elicitation | 2 | 3 | 4 | Medium | 3
Documentation of requirements | 2 | 3 | 4 | High | 4
Review requirements | 1 | 2 | 3 | Medium | 2
User Interface design
Initial Wireframe design | 3 | 4 | 5 | Medium | 4
Review of wireframe | 2 | 3 | 4 | Medium | 3
Create design based off feedback | 4 | 5 | 7 | High | 7
Review design | 2 | 3 | 4 | Low | 2
Software Design
Create design document | 2 | 5 | 8 | High | 8
Review of design | 1 | 3 | 5 | Medium | 3
Software Development
Development of software | 3 | 6 | 9 | High | 9
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 1 | 2 | 3 | Medium | 2
Execution of test cases | 5 | 6 | 7 | Medium | 6
System Integration Testing
Creation of System Integration Test Cases | 2 | 3 | 4 | Medium | 3
Execution of System Integration Test Cases | 5 | 6 | 8 | Medium | 6
Develop payment and accounting module
DBMS:
Install & Configure DBMS Engine & SQL Interface | 4 | 6 | 9 | High | 9
Test SQL interface software | 2 | 3 | 4 | Medium | 3
REST API Service Server:
Requirements
Requirements Elicitation | 2 | 3 | 4 | High | 4
Documentation of requirements | 3 | 5 | 6 | High | 6
Review requirements | 3 | 4 | 5 | Medium | 4
Software Design
Create design document | 2 | 5 | 6 | High | 6
Review of design | 2 | 3 | 4 | Medium | 3
Software Development
Development of software | 4 | 6 | 10 | High | 10
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 4 | 5 | 6 | Medium | 5
Client App:
Requirements
Requirements Elicitation | 2 | 3 | 4 | High | 4
Documentation of requirements | 5 | 6 | 7 | High | 7
Review requirements | 1 | 2 | 3 | Medium | 2
User Interface design
Initial Wireframe design | 3 | 4 | 5 | Medium | 4
Review of wireframe | 2 | 3 | 4 | Low | 2
Create design based off feedback | 2 | 4 | 6 | High | 6
Review design | 2 | 4 | 5 | Low | 2
Software Design
Create design document | 3 | 4 | 6 | High | 6
Review of design | 1 | 3 | 4 | Medium | 3
Software Development
Development of software | 4 | 6 | 8 | High | 8
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 2 | 5 | 6 | Medium | 5
System Integration Testing
Creation of System Integration Test Cases | 2 | 3 | 4 | Medium | 3
Execution of System Integration Test Cases | 3 | 4 | 5 | Medium | 4
Develop outgoing module
DBMS:
Install & Configure DBMS Engine & SQL Interface | 6 | 8 | 10 | Medium | 8
Test SQL interface software | 2 | 3 | 4 | Medium | 3
REST API Service Server:
Requirements
Requirements Elicitation | 3 | 4 | 6 | High | 6
Documentation of requirements | 5 | 7 | 8 | High | 8
Review requirements | 2 | 3 | 4 | Medium | 3
Software Design
Create design document | 3 | 5 | 7 | High | 7
Review of design | 1 | 3 | 5 | Medium | 3
Software Development
Development of software | 6 | 8 | 10 | High | 10
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 4 | 5 | 6 | Medium | 5
Client App:
Requirements
Requirements Elicitation | 4 | 6 | 8 | High | 8
Documentation of requirements | 5 | 6 | 7 | High | 7
Review requirements | 2 | 4 | 6 | Medium | 4
User Interface design
Initial Wireframe design | 3 | 4 | 5 | Low | 3
Review of wireframe | 1 | 2 | 3 | Low | 1
Create design based off feedback | 3 | 4 | 7 | High | 7
Review design | 2 | 3 | 4 | Medium | 3
Software Design
Create design document | 4 | 5 | 6 | High | 6
Review of design | 1 | 3 | 5 | Medium | 3
Software Development
Development of software | 6 | 7 | 10 | High | 10
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 3 | 5 | 6 | Medium | 5
System Integration Testing
Creation of System Integration Test Cases | 2 | 3 | 4 | Medium | 3
Execution of System Integration Test Cases | 4 | 5 | 6 | Medium | 5
Vulnerability Assessment
Execution of vulnerability scan | 5 | 8 | 10 | High | 10
Creation of reports | 1 | 2 | 3 | Medium | 2
Vulnerability remediation by development team | 4 | 5 | 8 | High | 8
Re-scan for vulnerabilities | 2 | 5 | 7 | High | 7
Final report created | 2 | 3 | 4 | Medium | 3
Performance Testing
Creation of Performance Test Cases | 3 | 5 | 8 | Medium | 5
Execution of test cases | 5 | 8 | 10 | Medium | 8
Regression Testing
Creation of regression suite of test cases | 3 | 4 | 7 | Medium | 4
Execution of regression suite | 6 | 7 | 9 | Medium | 7
User Acceptance Testing
Creation of User Acceptance Testing | 2 | 3 | 5 | Medium | 3
Execution of User Acceptance testing | 5 | 7 | 9 | Medium | 7
Client sign off for testing | 1 | 1 | 2 | Low | 1
System Training
Develop training materials and resources | 5 | 8 | 10 | Medium | 8
Staff training | 2 | 3 | 4 | Medium | 3
Staff workshops | 1 | 2 | 3 | Medium | 2
Deployment
Creation of rollout plan | 2 | 3 | 4 | High | 4
Review of roll out plan | 1 | 1 | 2 | High | 2
Dry-run of roll out plan | 1 | 1 | 2 | High | 2
Execution of rollout | 1 | 1 | 2 | High | 2
Warranty / Maintenance Period
Pay vendor invoices | 1 | 1 | 2 | Low | 2
Close out any open purchase orders | 1 | 2 | 4 | Low | 2
Conduct lessons learned | 1 | 1 | 2 | Medium | 2
Creation of support documentation | 2 | 4 | 6 | Medium | 5
Knowledge transfer of solution to support personnel | 3 | 5 | 8 | Medium | 6