## Sheet1
Task | Optimistic | Most Likely | Pessimistic | Risk | Estimate
Phase 1
Develop Appointment module
DBMS:
Install & Configure DBMS Engine & SQL Interface | 3 | 5 | 8 | Medium | 5
Test SQL interface software | 1 | 2 | 4 | Medium | 2
REST API Service Server:
Requirements
Requirements gathering | 2 | 3 | 4 | Medium | 3 | To Estimate Effort 1. Estimate the Optimistic, Most Likely, and Pessimistic task duration, if ONE PERSON was performing that task 2. Estimate the risk of each task  For example, the business analysis is high-risk, as we need to determine requirements with great care & attention to detail 3. Use the risk-factor to select the estimate  A high-risk task would use the most pessimistic estimate; a medium-risk the most likely estimate, and  A low-risk task would use the Optimistic estimate
Documentation of requirements | 3 | 4 | 5 | Medium | 4
Review requirements | 1 | 2 | 3 | Low | 1
Software Design
Create design document | 5 | 6 | 8 | High | 8
Review of design | 2 | 3 | 4 | Medium | 3
Software Development
Development of software | 5 | 8 | 12 | High | 12
Code Review | 2 | 3 | 4 | High | 4
Unit Testing
Creation of test cases | 1 | 2 | 3 | Medium | 2
Execution of test cases | 2 | 4 | 5 | Medium | 4
Client App:
Requirements
Requirements Elicitation | 3 | 5 | 6 | Medium | 5
Documentation of requirements | 3 | 4 | 5 | Medium | 4
Review requirements | 2 | 3 | 4 | Low | 2
User Interface design
Initial Wireframe design | 2 | 4 | 5 | Low | 2
Review of wireframe | 1 | 2 | 3 | Low | 1 |  | *This information is taken from the lecture slides
Create design based off feedback | 2 | 5 | 6 | High | 6
Review design | 1 | 2 | 3 | Low | 1
Software Design
Create design document | 3 | 5 | 6 | High | 6
Review of design | 2 | 3 | 4 | High | 4
Software Development
Development of software | 5 | 8 | 10 | High | 10
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 1 | 2 | 3 | Medium | 2
Execution of test cases | 3 | 4 | 5 | Medium | 4
System Integration Testing
Creation of System Integration Test Cases | 2 | 3 | 4 | Medium | 3
Execution of System Integration Test Cases | 5 | 6 | 7 | Medium | 6
Develop employee records module
DBMS:
Install & Configure DBMS Engine & SQL Interface | 4 | 7 | 10 | Medium | 7
Test SQL interface software | 2 | 3 | 4 | Medium | 3
REST API Service Server:
Requirements
Requirements Elicitation | 2 | 3 | 4 | High | 4
Documentation of requirements | 2 | 3 | 5 | Medium | 3
Review requirements | 2 | 3 | 5 | Medium | 3
Software Design
Create design document | 3 | 5 | 8 | High | 8
Review of design | 2 | 3 | 4 | High | 4
Software Development
Development of software | 5 | 8 | 12 | High | 12
Code Review | 2 | 3 | 4 | High | 4
Unit Testing
Creation of test cases | 1 | 2 | 3 | Medium | 2
Execution of test cases | 2 | 3 | 4 | Medium | 3
Client App:
Requirements
Requirements Elicitation | 2 | 3 | 4 | Medium | 3
Documentation of requirements | 2 | 3 | 4 | High | 4
Review requirements | 1 | 2 | 3 | Medium | 2
User Interface design
Initial Wireframe design | 3 | 4 | 5 | Medium | 4
Review of wireframe | 2 | 3 | 4 | Medium | 3
Create design based off feedback | 4 | 5 | 7 | High | 7
Review design | 2 | 3 | 4 | Low | 2
Software Design
Create design document | 2 | 5 | 8 | High | 8
Review of design | 1 | 3 | 5 | Medium | 3
Software Development
Development of software | 3 | 6 | 9 | High | 9
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 1 | 2 | 3 | Medium | 2
Execution of test cases | 5 | 6 | 7 | Medium | 6
System Integration Testing
Creation of System Integration Test Cases | 2 | 3 | 4 | Medium | 3
Execution of System Integration Test Cases | 5 | 6 | 8 | Medium | 6
Develop Patient records module
DBMS:
Install & Configure DBMS Engine & SQL Interface | 4 | 6 | 9 | High | 9
Test SQL interface software | 2 | 3 | 4 | Medium | 3
REST API Service Server:
Requirements
Requirements Elicitation | 2 | 3 | 4 | High | 4
Documentation of requirements | 3 | 5 | 6 | High | 6
Review requirements | 3 | 4 | 5 | Medium | 4
Software Design
Create design document | 2 | 5 | 6 | High | 6
Review of design | 2 | 3 | 4 | Medium | 3
Software Development
Development of software | 4 | 6 | 12 | High | 12
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 4 | 5 | 6 | Medium | 5
Client App:
Requirements
Requirements Elicitation | 2 | 3 | 4 | High | 4
Documentation of requirements | 5 | 6 | 7 | High | 7
Review requirements | 1 | 2 | 3 | Medium | 2
User Interface design
Initial Wireframe design | 3 | 4 | 5 | Medium | 4
Review of wireframe | 2 | 3 | 4 | Low | 2
Create design based off feedback | 2 | 4 | 6 | High | 6
Review design | 2 | 4 | 5 | Low | 2
Software Design
Create design document | 3 | 4 | 6 | High | 6
Review of design | 1 | 3 | 4 | Medium | 3
Software Development
Development of software | 4 | 6 | 8 | High | 8
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 2 | 5 | 6 | Medium | 5
System Integration Testing
Creation of System Integration Test Cases | 2 | 3 | 4 | Medium | 3
Execution of System Integration Test Cases | 3 | 4 | 5 | Medium | 4
Develop Inventory Management Module
DBMS:
Install & Configure DBMS Engine & SQL Interface | 6 | 8 | 10 | Medium | 8
Test SQL interface software | 2 | 3 | 4 | Medium | 3
REST API Service Server:
Requirements
Requirements Elicitation | 3 | 4 | 6 | High | 6
Documentation of requirements | 5 | 7 | 8 | High | 8
Review requirements | 2 | 3 | 4 | Medium | 3
Software Design
Create design document | 3 | 5 | 7 | High | 7
Review of design | 1 | 3 | 5 | Medium | 3
Software Development
Development of software | 6 | 8 | 10 | High | 10
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 4 | 5 | 6 | Medium | 5
Client App:
Requirements
Requirements Elicitation | 4 | 6 | 8 | High | 8
Documentation of requirements | 5 | 6 | 7 | High | 7
Review requirements | 2 | 4 | 6 | Medium | 4
User Interface design
Initial Wireframe design | 3 | 4 | 5 | Low | 3
Review of wireframe | 1 | 2 | 3 | Low | 1
Create design based off feedback | 3 | 4 | 7 | High | 7
Review design | 2 | 3 | 4 | Medium | 3
Software Design
Create design document | 4 | 5 | 6 | High | 6
Review of design | 1 | 3 | 5 | Medium | 3
Software Development
Development of software | 6 | 7 | 10 | High | 10
Code Review | 2 | 3 | 4 | Medium | 3
Unit Testing
Creation of test cases | 2 | 3 | 4 | Medium | 3
Execution of test cases | 3 | 5 | 6 | Medium | 5
System Integration Testing
Creation of System Integration Test Cases | 2 | 3 | 4 | Medium | 3
Execution of System Integration Test Cases | 4 | 5 | 6 | Medium | 5